## Sheet1
Task title	Modules	Expected complexity	Hours required	% Completed
Process a single record	CDRProcessor, Processor	1	2	100.00%
Accumulate a single record	CDRProcessor, Accumulator	1	2	100.00%
Transmit record from Feeder to CDRProcessor	Feeder, FeederClient, Transmitter	3	5	80.00%
CDRProcessor receive record from Feeder	CDRProcessor, FeederServer, Receiver	3	5	40.00%
Process multiple records	CDRProcessor, Processor	3	5	0.00%
Accumulate multiple records	CDRProcessor, Accumulator, Container	3	5	0.00%
Read CDR data from file	Feeder, FileManager, Reader	3	5	0.00%
Parse CDR data into Msg	Feeder, Parser	3	5	15.00%
Send command from UI to run	UI, UIClient, CDRProcessor, Feeder, UIServer	4	6	10.00%
Send command from UI to print report to screen	UI, Accumulator, ExportManager	4	6	0.00%
Send command from UI to produce report file	UI, Accumulator, ExportManager	4	6	0.00%
Detect a new CDR file in ‘Working’ directory	Feeder, FileManager	4	6	0.00%
Move finished CDR file from ‘Working’ to ‘Done’	Feeder, FileManager	4	6	0.00%